## Audit Report
Phase | Category | ID | File | Issue | Severity | Status | Fix
Phase 1 | Critical Security | F1 | whatsapp-crm/src/stores/authStore.ts:47-66 | Master auth bypass - hardcoded credentials in client bundle | Critical | Done | Removed master auth bypass. Master now uses Supabase Auth via backend
Phase 1 | Critical Security | F2 | whatsapp-crm/src/components/Header.tsx:36-46 | WhatsApp access tokens exposed to client | Critical | No | Move Meta API calls to server-side proxy endpoint
Phase 1 | Critical Security | F3 | whatsapp-crm/src/components/AdminProtectedRoute.tsx:24 | Role mismatch - checks 'super_admin' but type has 'master' | Critical | Done | Added 'master' to allowed roles
Phase 1 | Critical Security | F4 | whatsapp-crm/.env + authStore.ts | Hardcoded master credentials in client bundle | Critical | Done | Removed all hardcoded credentials from frontend
Phase 1 | Critical Security | B1 | backend/src/config/whatsappConfig.js:5 | Hardcoded access_token as fallback in source code | Critical | Done | Removed all hardcoded fallback secrets
Phase 1 | Critical Security | B2 | backend/src/controllers/authController.js:13-16 | Hardcoded admin credentials compared in plaintext | Critical | No | Hash stored credentials. Add account lockout
Phase 1 | Critical Security | B3 | backend/src/controllers/froWhatsAppAuthController.js:55 | rpc_ token is unsigned - anyone can impersonate users | Critical | Done | Replaced rpc_ prefix with proper signed JWT
Phase 1 | Critical Security | B4 | backend/src/index.js:442-452 | /api/debug unauthenticated - exposes DB internals | Critical | Done | Added authenticate middleware
Phase 1 | Critical Security | B5 | backend/src/index.js:135-145 | /api/upload unauthenticated - arbitrary file upload | Critical | Done | Added authenticate + MIME type allowlist
Phase 1 | Critical Security | B6 | backend/src/index.js:375-381 | CRON auth bypass when API key unset | Critical | Done | Returns 503 if CRON_API_KEY not set
Phase 1 | Critical Security | B7 | backend/src/controllers/whatsappMessageController.js | Supabase service_key exposed in HTTP calls | Critical | No | Use Supabase client library instead
Phase 1 | Critical Security | B8 | backend/src/controllers/workerController.js:63,115 | Default worker password is '123456' | Critical | Done | Generate random 12-char passwords
Phase 1 | Critical Security | B9 | backend/src/index.js:64-71 | CORS origin: '*' fallback | Critical | Done | Removed '*' fallback, warns on startup
Phase 1 | Critical Security | B10 | backend/src/controllers/froWhatsAppAuthController.js | Master login returns no JWT token | Critical | Done | Issues proper signed JWT for master
Phase 2 | High Security | BH1 | ALL backend controllers | No input validation library | High | No | Install zod/joi, add schemas
Phase 2 | High Security | BH2 | userController.js, webhookController.js | Mass assignment via req.body spread | High | No | Create whitelistFields() utility
Phase 2 | High Security | BH3 | accountsController.js:895-912 | Destructive receipt import - DELETE ALL then insert | High | No | Replace with upsert + transaction
Phase 2 | High Security | BH4 | accountsController.js:145-153 | Race condition in verifyLead - read-modify-write | High | No | Use atomic RPC increment
Phase 2 | High Security | BH5 | ALL backend controllers | Error messages leak internal details | High | Done | Created sanitizeError utility, generic messages
Phase 2 | High Security | BH6 | ALL routes except authRoutes | No rate limiting on endpoints | High | No | Add global rate limiter
Phase 2 | High Security | BH7 | authController.js:64-92 | Missing is_active check on login | High | Done | Added is_active check, returns 403
Phase 2 | High Security | BH8 | index.js:329-330 | Failed Meta send marks 'sent' not 'failed' | High | Done | Changed to 'failed' with failure_reason
Phase 2 | High Frontend | FH1 | whatsapp-crm/tsconfig.json:14 | TypeScript strict mode disabled | High | No | Enable strict:true
Phase 2 | High Frontend | FH2 | QuickReplyBar.tsx, Header.tsx | Empty catch blocks silently swallow errors | High | Done | Added console.error in both catch blocks
Phase 2 | Auth Overhaul | A1 | authController.js (all jwt.sign) | No client-type JWT expiry differentiation | Critical | Done | X-Client-Type header: Flutter=100y, Web=24h
Phase 2 | Auth Overhaul | A2 | authMiddleware.js:34 | authenticateAdmin missing 'master' role | Critical | Done | Added 'master' to authenticateAdmin
Phase 2 | Auth Overhaul | A3 | authStore.ts (all paths) | Frontend stores rpc_/Supabase JWT, not backend JWT | High | Done | Auth now goes through backend API, stores backend JWT
Phase 2 | Auth Overhaul | A4 | index.js:113 | /api/whatsapp/fro-login has NO auth middleware | High | No | Add rate limiting
Phase 3 | API Routing - Auth | R1 | whatsapp-crm authStore.ts | Auth done via Supabase directly | High | Done | Created backend /api/whatsapp-crm/auth/* endpoints
Phase 3 | API Routing - Auth | R2 | authStore.ts (RPC calls) | supabase.rpc calls for user management client-side | High | Done | Backend proxies all RPC calls, frontend only gets token
Phase 3 | API Routing - Messages | R3 | whatsapp.ts + InboxPage.tsx (~21 calls) | Messages table queried directly from Supabase | High | No | Create GET/POST /api/whatsapp/messages endpoints
Phase 3 | API Routing - Conversations | R4 | whatsapp.ts + InboxPage.tsx (~16 calls) | Conversations table queried directly | High | No | Create GET/PUT /api/whatsapp/conversations endpoints
Phase 3 | API Routing - Contacts | R5 | whatsapp.ts + ContactsPage.tsx (~17 calls) | Contacts table queried directly | High | No | Create GET/POST/PUT /api/whatsapp/contacts endpoints
Phase 3 | API Routing - Accounts | R6 | whatsapp.ts + metaCredentials.ts (~26 calls) | whatsapp_accounts with access tokens queried directly | Critical | No | Create /api/whatsapp/accounts, move token fetch server-side
Phase 3 | API Routing - Assignments | R7 | whatsapp.ts + InboxPage.tsx (~11 calls) | agent_phone_assignments queried directly | High | No | Create /api/whatsapp/assignments endpoints
Phase 3 | API Routing - Templates | R8 | TemplatesPage.tsx + TemplateEditorPage.tsx (~8 calls) | whatsapp_templates queried directly | High | No | Create /api/whatsapp/templates endpoints
Phase 3 | API Routing - Quick Replies | R9 | SettingsPage.tsx + QuickReplyBar.tsx (~5 calls) | quick_replies queried directly | Medium | No | Create /api/whatsapp/quick-replies endpoints
Phase 3 | API Routing - Users | R10 | metaCredentials.ts + TeamMemberPage.tsx (~6 calls) | users table queried directly | High | No | Create /api/whatsapp/users endpoints
Phase 3 | API Routing - Tenants | R11 | metaCredentials.ts + admin pages (~8 calls) | tenants table queried directly | Medium | No | Create /api/whatsapp/tenants endpoints
Phase 3 | API Routing - Deals/Pipeline | R12 | AnalyticsPage.tsx + PipelineBoard.tsx (~5 calls) | deals/pipelines queried directly | Medium | No | Create /api/whatsapp/deals endpoints
Phase 3 | API Routing - Automations | R13 | FlowBuilderPage.tsx + AutomationsPage.tsx (~5 calls) | automation_flows queried directly | Medium | No | Create /api/whatsapp/automations endpoints
Phase 3 | API Routing - Media/Storage | R14 | SettingsPage.tsx + MediaLibrary.tsx (~9 calls) | media_library + storage called directly | Medium | No | Create /api/whatsapp/media endpoints
Phase 3 | API Routing - API Keys | R15 | SettingsPage.tsx (~4 calls) | api_keys queried directly | High | No | Create /api/whatsapp/api-keys endpoints
Phase 3 | API Routing - FRO Assignments | R16 | TeamMemberPage.tsx + TeamPage.tsx (~5 calls) | fro_whatsapp_assignments queried directly | Medium | No | Create /api/whatsapp/fro-assignments endpoints
Phase 3 | API Routing - Workers | R17 | TeamMemberPage.tsx (1 call) | workers table queried directly | Medium | No | Route through /api/workers
Phase 3 | API Routing - Webhook Logs | R18 | AdminWebhookPage.tsx (1 call) | whatsapp_webhook_logs queried directly | Low | No | Create /api/whatsapp/webhook-logs endpoint
Phase 3 | API Routing - Realtime | R19 | whatsapp.ts (2 channel subscriptions) | Supabase Realtime channels subscribed directly | Medium | No | Keep Supabase Realtime for now (complex to proxy)
Phase 4 | Medium Backend | M1 | ALL backend controllers | No structured logging | Medium | No | Install pino/winston, add request IDs
Phase 4 | Medium Backend | M2 | backend/src/index.js | No /health endpoint | Medium | No | Add GET /api/health
Phase 4 | Medium Backend | M3 | dashboardController.js:43-46 | Unbounded queries - no pagination | Medium | No | Add pagination
Phase 4 | Medium Backend | M4 | dashboardController.js:90-98 | N+1 query pattern for NGOs | Medium | No | Single optimized query with joins
Phase 4 | Medium Backend | M5 | index.js:135-338 | ~200 lines inline in index.js | Medium | No | Extract to whatsappSendController.js
Phase 4 | Medium Backend | M6 | froController.js (1400+ lines) | God file - too many responsibilities | Medium | No | Split into focused controllers
Phase 4 | Medium Backend | M7 | accountsController.js:79-219 | Missing transaction handling in verifyLead | Medium | No | Wrap in RPC transaction
Phase 4 | Medium Backend | M8 | index.js:135-145 | No file type validation on upload | Medium | Done | Added MIME type allowlist
Phase 4 | Medium Backend | M9 | emailConfig.js:14 | TLS verification disabled | Medium | No | Set rejectUnauthorized: true
Phase 4 | Medium Backend | M10 | superAdminController.js:70-89 | No auth check on target updates | Medium | No | Verify worker belongs to org
Phase 4 | Medium Frontend | MF1 | DashboardPage.tsx:10 | Meta API version v19.0 vs v23.0 | Medium | No | Standardize to v23.0
Phase 4 | Medium Frontend | MF2 | ContactDetailPage.tsx:41-43 | Shows Loading on error | Medium | No | Check error state
Phase 4 | Medium Frontend | MF3 | AudioRecorder.tsx:24-28 | Stale closure in cleanup | Medium | No | Use useRef
Phase 4 | Medium Frontend | MF4 | TemplateBar.tsx:44 | No HTTP status check on Meta response | Medium | No | Check res.ok first
Phase 4 | Medium Frontend | MF5 | InboxPage.tsx (~1000+ lines) | Monolith component | Medium | No | Break into smaller components
Phase 5 | Low - Code Quality | L1 | whatsapp-crm/ | No test files - zero coverage | Medium | No | Add unit + integration tests
Phase 5 | Low - Code Quality | L2 | index.js:59 | Unused import _log | Low | No | Remove unused variable
Phase 5 | Low - Code Quality | L3 | froController.js:240,289 | Duplicate todayStr variable | Low | No | Remove duplicate
Phase 5 | Low - Code Quality | L4 | froController.js:464 | Hardcoded magic numbers | Low | No | Move to settings
Phase 5 | Low - Code Quality | L5 | ALL controllers | Missing JSDoc annotations | Low | No | Add JSDoc types
Phase 5 | Low - Code Quality | L6 | whatsappController.js:171-177 | Rejected promises silently converted | Low | No | Add retry logic
Phase 5 | Low - Code Quality | L7 | froRoutes.js:55-73,86-105 | Inline queries in route handlers | Low | No | Move to controllers
Phase 5 | Low - Code Quality | L8 | metaCredentials.ts:3-6 | Module-level cache never reset | Low | No | Reset on auth changes
NB1 | Backend message CRUD endpoints | Critical | Messages | Created /api/whatsapp-crm/messages (GET, POST, PUT) with auth middleware | Done | whatsappCrmDataController.js, whatsappCrmDataRoutes.js
NB2 | Backend conversation CRUD endpoints | Critical | Conversations | Created /api/whatsapp-crm/conversations (GET, POST, PUT) with auth middleware | Done | whatsappCrmDataController.js, whatsappCrmDataRoutes.js
NB3 | Message count endpoints | High | Dashboard | Created /api/whatsapp-crm/messages/counts with daily/monthly/total counts | Done | whatsappCrmDataController.js
NB4 | Conversation count endpoints | High | Dashboard | Created /api/whatsapp-crm/conversations/counts with total/open/closed | Done | whatsappCrmDataController.js
NB5 | Frontend api.ts helper | High | Frontend | Created centralized API helper with auth token injection for all backend calls | Done | whatsapp-crm/src/lib/api.ts
NB6 | whatsapp.ts backend routing | Critical | Frontend | Updated sendWhatsAppMessage and sendWhatsAppTemplate to use backend API for message/conversation operations | Done | whatsapp.ts
NB7 | DashboardPage backend routing | High | Frontend | Replaced 8 direct Supabase count queries with fetchMessageCounts/fetchConversationCounts | Done | DashboardPage.tsx
NB8 | InboxPage backend routing | Critical | Frontend | Replaced conversations list, messages, and creation calls with backend API | Done | InboxPage.tsx
NB9 | MessageComposer backend routing | High | Frontend | Replaced message insert calls with createMessage API | Done | MessageComposer.tsx
NB10 | Admin pages backend routing | Medium | Frontend | Replaced tenant detail and admin dashboard count queries with backend API | Done | AdminTenantDetailPage.tsx, AdminDashboardPage.tsx
NB11 | QuickReplyBar/TemplateBar routing | Medium | Frontend | Replaced conversation lookups with fetchConversation API | Done | QuickReplyBar.tsx, TemplateBar.tsx
NB12 | Message count total field | High | Backend | Added total count to getMessageCounts for admin dashboard | Done | whatsappCrmDataController.js
NB13 | whatsappMessageController key fix | High | Security | Removed SUPABASE_ANON_KEY fallback from service key; added env guard | Done | whatsappMessageController.js

## Summary
Metric | Value
Total Issues | 70
Critical | 17
High | 21
Medium | 24
Low | 8
DONE | 21
NOT DONE | 49
Phase 1 (Critical Security) | 11/14 done
Phase 2 (Auth + High) | 7/14 done
Phase 3 (API Routing) | 2/19 done
Phase 4 (Medium) | 1/15 done
Phase 5 (Code Quality) | 0/8 done